## April 1
|  |  | Weekly Sprint Sheet |  | Team Members | Email
Project: Trivia |  |  |  |  | Saema Ansari | sansar27@uic.edu
Week Of: 04/21/2019 |  |  |  |  | James Iorgovan | jiorgo2@uic.edu
Team number: 12 |  |  |  |  | Michelle Baginski | mbagin3@uic.edu
[5 empty] | Kirun Haque | khaque3@uic.edu
Completed
In Progress
Incomplete/Need help!
Action Item | Item ID | Team Member | Last Week | This Week | Next Week | Issues
Create a text file that list all the questions and their answer choices(first answer is the correct answer) | 1 | Everyone | Create a text file with questions. The question will be on the first line. The correct answer on the following line, and 2 incorrect answers following those lines. | Completed task | N\A | No issues. Just have to make sure that there's no white space between each line and at the end of the file
First line on the text file will be trivia question. The next line will be the correct answer to that question. The lines after that will be 2 incorrect answers. Store into hashmap String to ArrayList<String>. Put this file in the client code. | 2 | Kirun Haque | Do research on how to extract from a text file and somehow put in a hashmap. First line is the question(KEY) and the next 3 lines will be an ArrayList and repeat | Completed task | N\A | The issues I ran into was finding where the file was located. writing "src/filename" solved my issue
Randomly generate a question and send to a client and display it on the client GUI | 3 | Saema Ansari | Create a hasmap(int, string) in server that maps a number to each question in question bank. Then use rand to randomly generate a question number and send to clients. Screen reader support enabled. | Display the question recieved with all of it's answer choices on the client GUI. Make sure a question displayed once is not displayed again until the end of the game. | Task completed. Nothing to do | No issues. Just had to store the used question numbers in an array and make sure used questions are not asked again.
insert pictures for the correct answer after the client have answered a question stating if their answer was correct or not + the string of the correct answer | 4 | Michelle Baginski | Find the images that will be used. | Completed task | Completed. | No issues. I used two hashmaps. One maps a question to the corresponding question number, and the other maps a string to a label containing the image for that question.
Make sure only 4 clients can connect to the server | 5 | Kirun Haque | Use i < 4 for the while loop so it doesn't listen infinitely in the server code | Completed task | N\A | No issues
Get username (will use from previous program: RPSLS) | 6 | Kirun Haque | Use previous program's logic. By asking the user for username after connecting to the server | Completed task | This should be completed in the first week, since it's already implemented from previous program | No issues
Notify players once 4 clients are connected and display questions | 7 | James Iorgovan | N\A | Send a message from the server to initiate the client games | Testing. | No issues
|  | Michelle Baginski completed the task above |  |  | Completed.
Calculate rankings in server code and send it to all clients | 8 | Saema Ansari | Create a function that takes all players' scores and assign their ranks | Notify client's of their rank. Reset scores | Task completed. Nothing to do | Figuring out how to rank the players with ties was difficult
Create server GUI | 9 | Michelle Baginski | Create the initial GUI for the server. Allow players to connect. | Completed task | N\A | No issues.
Play again button in Client GUI Quit button in Client GUI | 10 | James Iorgovan | N\A | Reset scores, questions, any game state variables. Exit game option at beginning of game and at the end, in beginning make sure once game starts button is not visible anymore | Test and tie up loose ends Task completed
Updated Exit button | 11 | Kirun Haque | N\A | Closed the connection before Platform.exit() and updated server so the correct number of clients can show on the server gui. And also made sure that 4 clients can connect to the server after 4 players are finished playing a game | Task completed | Figuring how to send a message to the other clients when another client dropped during a game was difficult. After trial and error, I sent the message in the catch statement in the ClientThread class.
Notified the player other client's usernames as each client connects to the server and gets approved username | 12 | Kirun Haque | Implemented similar logic from program 4 | Completed task | N\A | No issues, because I implemented a similar logic I did in the RPSLS program
Make generic event handler for multiple choice answers, so the program knows which button the client pressed since the order of the buttons will be different for each question. Also, create multi choice answers for the buttons | 13 | Kirun Hauqe | Made a event handler called triviaBtn which will check the if user answered the question correctly. Also, made an array of Buttons and set them on action with the corresponding event handler. | Completed task | N\A | The issues I had was finding the correct place to instantiate the 3 buttons that can be reused for every single question
Project design document | 14 | Kirun Haque | Create the project design document | Start the document | Task Completed | No issues.
Activity Diagram | 15 | Saema Ansari | Learn about activity diagram | Create the activity diagram for Server and Client programs | Task Completed | No issues.
UML diagrams for client & server | 16 | Michelle Baginski | Create the UML diagrams | Create the UML for both Server and Client | Task Completed | No issues.