## April 1
|  |  | Weekly Sprint Sheet |  | Team Members | Email
Project: Trivia |  |  |  |  | Saema Ansari | sansar27@uic.edu
Week Of: 04/15/2019 |  |  |  |  | James Iorgovan | jiorgo2@uic.edu
Team number: 12 |  |  |  |  | Michelle Baginski | mbagin3@uic.edu
[5 empty] | Kirun Haque | khaque3@uic.edu
Completed
In Progress
Incomplete/Need help!
Action Item | Item ID | Team Member | Last Week | This Week | Next Week | Issues
Create a text file that list all the questions and their answer choices(first answer is the correct answer) | 1 | Everyone | N\A | Create a text file with questions. The question will be on the first line. The correct answer on the following line, and 2 incorrect answers following those lines. | Finish the trivia question list, no more should be added
First line on the text file will be trivia question. The next line will be the correct answer to that question. The lines after that will be 2 incorrect answers. Store into hashmap String to ArrayList<String>. Put this file in the client code. | 2 | Kirun Haque | N\A | Do research on how to extract from a text file and somehow put in a hashmap. First line is the question(KEY) and the next 3 lines will be an ArrayList and repeat | If I don't figure it out this week, ask for help or hard code questions and list into a hashmap for a small pool of questions
Randomly generate a question and send to a client and display it on the client GUI | 3 | Saema Ansari | N\A | Create a hasmap(int, string) in server that maps a number to each question in question bank. Then use rand to randomly generate a question number and send to clients. | Display the question recieved with all of it's answer choices on the client GUI. Make sure a question displayed once is not displayed again until the end of the game.
insert pictures for the correct answer after the client have answered a question stating if their answer was correct or not + the string of the correct answer | 4 | Michelle Baginski | N\A | Find the images that will be used. | Update images if list of trivia questions is updated
Make sure only 4 clients can connect to the server | 5 | Kirun Haque | N\A | Use i < 4 for the while loop so it doesn't listen infinitely in the server code | This is already completed
Get username (will use from previous program: RPSLS) | 6 | Kirun Haque | N\A | Use previous program's logic. By asking the user for username after connecting to the server | This should be completed in the first week, since it's already implemented from previous program
Notify players once 4 clients are connected and display questions | 7 | James Iorgovan | N\A | Send a message from the server to initiate the client games | Testing.
Calculate winner in server code and send it to all clients | 8 | Saema Ansari | N\A | Create a function that takes all players' scores and assign their ranks | Notify client's of their rank. Reset scores
Create server GUI | 9 | Michelle Baginski | N\A | Create the initial GUI for the server. Allow players to connect. | Do testing to make sure everything works accordingly
Play again button in Client GUI | 10 | James Iorgovan | N\A | Reset scores, questions, any game state variables. | Test and tie up loose ends